NORTHSTAR SPRINT
TEAM CHARTER & PROJECT BOARD

Purpose: This is the team's Day 1 working Charter and Project Board. It preserves the 10 tasks agreed upon by the team and adds the governance, Definition of Done, evidence, status, and audit requirements needed by the assessment.

# 1. Client & Project Context

Northstar Retail Co. is a mid-size e-commerce company whose support team is overloaded by repetitive questions about order status, returns/refunds, and stock availability. The team has one week to build an MVP that demonstrates a support-deflection approach rather than a finished production product.

Assessment requirement: the MVP must reduce manual ticket handling for at least two of the three ticket categories and be demoable end-to-end. The assessment also requires a one-page go-live readiness note and a collaborative commit/edit audit trail.

# 2. Team Seats & Responsibilities

| Seat | Name | Primary board responsibility | Required collaboration |
| --- | --- | --- | --- |
| Member 1 | Nahom Tesfa | Team Charter and Project Board Setup | Coordinate charter decisions, maintain board discipline, and compile traceability evidence for final handoff readiness. |
| Member 2 | Eunice Livingproof | Repo / Workspace Creation, Codebase Implementation | Establish shared workspace and communicate the technical/product approach. |
| Member 3 | Hesborn Ombeka | Streamlit Implementation, Dashboard Implementation | Build the core implementation and working application. |
| Member 4 | Masombo Audrey | Strategy Deck, Project Report | Build the team strategy and document the project outcome. |
| Member 5 | Faith Musyoka | Audit Log Compilation, Go-Live 1-Pager | Manage audit log integrity and ensure the Go-Live note accurately reflects final delivery status. |

# 3. Project Mission & Success Criteria

Mission: Deliver a small, working Support Deflection MVP and a complete evidence trail showing that five team members planned, built, documented, and audited the work collaboratively.

| Success criterion | Acceptance signal |
| --- | --- |
| Working MVP | At least two ticket types are covered and the agreed MVP can be demonstrated end-to-end. |
| Ten-task board | All 10 agreed tasks are represented with owner, priority, estimate, status, and Definition of Done. |
| Task sizing | Every task is scoped to 4 hours or less. |
| Same-day board discipline | Status changes are reflected on the live board on the same day work occurs. |
| Traceability | Board work can be mapped to actual commits/edits and timestamps. |
| Go-live readiness | The one-page note states what works, known-broken/limited items, and handoff steps. |

# 4. Scope & Agreed Product Work

The team has agreed to retain the following project-board structure:

Selected ticket categories / final MVP scope: Order status, Returns/refunds, and Stock availability

Technology approach: [INSERT THE TEAM'S AGREED TECHNOLOGY STACK / ARCHITECTURE]

Important scope rule: the board contains exactly 10 tasks. Any work discovered during execution that is necessary but not represented by a task must be handled according to the team's change-control rule below rather than silently creating large, untraceable work.

# 5. Team Working Agreement

- The 10 board tasks are the team's agreed units of work; no task may exceed four hours under the anti-black-box rule.

- Each task has one accountable owner. Other members may collaborate, review, test, or provide support, but ownership remains visible.

- The live board is updated on the same day that work occurs.

- Every meaningful commit/edit follows: <type>: <what changed> - <why it matters>.

- Messages such as 'wip,' 'updates,' or 'changes' are not acceptable audit evidence.

- Blockers are reported as soon as they occur and are not hidden until the deadline.

- Evidence must be preserved as work happens; the team will not reconstruct an artificial history at the end.

- The team prioritizes completion of the working MVP and assessment evidence over unnecessary feature expansion.

- The confidential Peer Reliability Index is completed individually and is not shared verbatim between teammates.

# 6. Communication, Deadlines & Conflict Resolution

| Area | Team rule |
| --- | --- |
| Primary communication | WhatsApp group |
| Project board | Project Board |
| Repository / workspace | Repository / Workspace |
| Daily status discipline | The owner updates the live board on the same day work occurs; this is checked during the end-of-day Google Meet recap. |
| Blockers | The owner flags the blocker immediately in the agreed team channel and on the board where applicable. |
| Deadline management | The team reviews progress against the five-day timeline and prioritizes blocked/high-risk work first. |
| Technical disagreement | Members present evidence/options; the responsible owner proposes the decision; the team agrees on the final direction. |
| Priority disagreement | Project/product coordination resolves the conflict using MVP value, deadline risk, and assessment requirements. |
| Missed commitment | The owner explains the blocker and proposes a recovery action, and the team records any reassignment/support decision. |
| Persistent inactivity | Two or more days of zero visible activity triggers the Charter escalation path immediately. |

# 6A. Decision-Making Process

The team will use a clear, evidence-based decision process so that technical, scope, and deadline decisions are made quickly without creating unnecessary conflict.

| Decision type | Process | Final decision owner |
| --- | --- | --- |
| Routine implementation decision | The task owner may decide within the agreed scope and inform the team in the WhatsApp group. | Task owner |
| Technical decision affecting another task | Discuss with affected owner(s); agree on the option that best protects the MVP, timeline, and integration. | Relevant task owners: Project/product coordination resolves deadlock. |
| Scope / feature decision | Check whether the change is necessary for the MVP and whether it fits the agreed task scope and four-hour anti-black-box rule. | Project/Product Lead with team input |
| Priority / deadline decision | Review impact on delivery, assessment requirements, and dependencies; highest-risk/highest-value work takes precedence. | Project/Product Lead |
| Conflict or deadlock | Discuss facts and alternatives; each side gets a chance to explain its position; seek consensus first. If consensus cannot be reached, the designated lead makes the final call and records the decision. | Project/Product Lead |

# 6B. Communication Plan

The team will use WhatsApp as the primary day-to-day communication channel and Google Meet for an end-of-day recap meeting. The purpose is to keep fast communication separate from the formal project evidence recorded on the board and in the repository/workspace.

| Communication activity | Channel | Timing | Purpose | Expected output |
| --- | --- | --- | --- | --- |
| Day-to-day coordination | WhatsApp group | As needed throughout the day | Questions, quick updates, blockers, coordination, and urgent decisions. | Relevant decision/blocker/update communicated to the team. |
| End-of-day recap | Google Meet | End of each working day | Review what was completed, what is still in progress, blockers, next actions, and whether the board reflects the day's work. | Short recap; task statuses confirmed/updated the same day. |
| Task evidence | Project board + repository/workspace | Same day as work | Maintain the formal audit trail. | Updated status and traceable commit/edit evidence. |
| Major decision | WhatsApp + end-of-day Google Meet | When decision occurs / recap same day | Ensure the team understands important scope, technical, or deadline decisions. | Decision and rationale communicated; relevant board/task documentation updated. |

# 6C. Ground Rules & Team Norms

- Respect every team member's contribution and allow others to finish explaining their position before responding.

- Keep communication professional, direct, and solution-focused; disagreements are about the work, not the person.

- Respond to important WhatsApp messages and blocker requests in a reasonable time during agreed working hours.

- Do not disappear when blocked. Notify the team early and state what help or decision is required.

- Own assigned tasks from start to Definition of Done, while asking for help when necessary.

- Keep the live board accurate on the same day the work happens.

- Use the required commit/edit convention and avoid meaningless messages such as 'wip,' 'updates,' or 'changes.'

- Do not claim work that another member completed; contribution must remain accurately attributable.

- Do not create artificial or retrospective evidence. Audit records must reflect the actual work history.

- Keep the end-of-day Google Meet recap focused and practical: completed work, blockers, decisions, and next steps.

- Respect the confidentiality of the Peer Reliability Index; individual responses must not be shared verbatim between teammates.

# 6D. Conflict Resolution Process

Conflicts are expected to be handled early and professionally. The goal is to resolve the issue without delaying the MVP or damaging the team's working relationship.

| Step | Action |
| --- | --- |
| 1. Identify | The people involved clearly state the issue, the specific point of disagreement, and the effect on the task/project. |
| 2. Discuss | The parties discuss the issue directly and respectfully, using requirements, evidence, deadlines, and task ownership rather than personal opinions. |
| 3. Seek consensus | The team considers the available options and selects the solution that best protects the MVP requirements, quality, and deadline. |
| 4. Escalate if unresolved | If the disagreement cannot be resolved, the Project/Product Lead facilitates a final discussion and makes the decision where necessary. |
| 5. Record | If the conflict changes a task, priority, scope, dependency, or technical direction, the resulting decision is recorded in the appropriate project documentation/board and communicated to the team. |
| 6. Recover | If the conflict caused delay or blocked work, the owner and team agree on a recovery action and update the board accordingly. |

# 6E. Charter Acceptance

By signing/confirming below, each member agrees to follow the communication plan, decision-making process, ground rules, conflict-resolution process, task ownership, and audit requirements in this Charter.

| Member | Confirmation / Signature | Date |
| --- | --- | --- |
| Nahom Tesfa | [Confirm] | [Date] |
| Eunice Livingproof | [Confirm] | [Date] |
| Hesborn Ombeka | [Confirm] | [Date] |
| Masombo Audrey | [Confirm] | [Date] |
| Faith Musyoka | [Confirm] | [Date] |

# 7. Board Status Definitions

| Status | Meaning |
| --- | --- |
| Backlog | Task is defined but work has not started. |
| In Progress | Owner is actively working on the task. |
| Blocked | A dependency, decision, access issue, or defect prevents progress. |
| Review / QA | Work is sufficiently complete for review/testing. |
| Done | The task's Definition of Done is satisfied and supporting evidence exists. |

# 8. Definition of Done Standard

Each Definition of Done is a single, checkable sentence. A task is not marked "Done" merely because the owner has spent the estimated time; the stated outcome must be achieved, and evidence must exist.

# 9. PROJECT BOARD—AGREED 10 TASKS

| # | Task | Owner | Priority | Est. | Status | Definition of Done |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Team Charter | Member 1 | High | 1.5h | Backlog | Charter drafted covering communication, deadlines, and conflict resolution; shared with all 5 seats for signature. |
| 2 | Project Board Setup | Member 1 | High | 2h | Backlog | All 10 tasks entered on the board, each tagged with owner, priority, estimate, status, and Definition of Done. |
| 3 | Repo / Workspace Creation | Member 2 | High | 1h | Done | Shared repo/workspace created with README and branch-naming convention documented; all 5 seats added as collaborators. |
| 4 | Strategy Deck | Member 4 | Medium | 2h | Backlog | 5–7 slide deck covering the problem, chosen ticket categories, and tech approach, ready for team review. |
| 5 | Codebase Implementation | Member 2 | High | 3h | Backlog | Order-status lookup returns a correct result for 3 sample order IDs, end-to-end. |
| 6 | Streamlit Implementation | Member 3 | High | 2h | Backlog | Streamlit app runs locally and renders a working input form for at least one ticket category. |
| 7 | Dashboard Implementation | Member 3 | Medium | 2h | Backlog | Self-serve dashboard displays working views for order status, returns, and stock availability. |
| 8 | Project Report | Member 4 | Low | 2h | Backlog | Draft report covering problem, approach, and results is complete and ready for review. |
| 9 | Audit Log Compilation | Member 5 | High | 1.5h | Backlog | Commit/edit history and board timestamps exported into a single audit file with no unexplained gaps. |
| 10 | Go-Live 1-Pager | Member 5 | High | 1h | Backlog | One page listing what works, what is known-broken, and handoff steps is complete. |

# 10. Task-by-Task Execution & Evidence Requirements

| Task | What the owner should produce | Minimum evidence to preserve |
| --- | --- | --- |
| 1 — Team Charter | Final agreed charter covering communication, deadlines, conflict resolution, roles, and working rules. | Charter document + team confirmations/signatures + timestamp. |
| 2 — Project Board Setup | Live board containing exactly the 10 agreed tasks with required fields. | Board screenshot/export + task history/timestamps. |
| 3 — Repo / Workspace Creation | Shared workspace, README, branch convention, and all five collaborators. | Repository/workspace link + README/setting evidence + creation/access timestamp. |
| 4 — Strategy Deck | 5–7 slides explaining problem, selected categories, and technical approach. | Deck file/version history + review evidence. |
| 5 — Codebase Implementation | Working order-status lookup using three sample order IDs. | Commit/edit reference + test evidence + demo result. |
| 6 — Streamlit Implementation | Locally running Streamlit app with a working input form for at least one ticket category. | Commit/edit reference + run/test evidence. |
| 7 — Dashboard Implementation | Dashboard views for order status, returns, and stock availability. | Commit/edit reference + screenshots/demo evidence. |
| 8 — Project Report | Draft report covering problem, approach, and results. | Report file/version history + review evidence. |
| 9 — Audit Log Compilation | Single audit file containing commit/edit history and board timestamps. | Raw exported logs + compiled audit file. |
| 10 — Go-Live 1-Pager | One-page handoff/readiness note. | Final one-page document + timestamp/version evidence. |

# 11. Commit / Edit Convention

Required format:

<type>: <what changed> - <why it matters>

Recommended examples:

- docs: add team charter - defines communication and conflict-resolution rules

- chore: configure project board - establishes the ten agreed sprint tasks

- chore: initialize repository - gives the team a shared workspace and branch convention

- docs: add strategy deck - communicates the selected support-deflection approach

- feat: implement order lookup - returns status for the three agreed sample orders

- feat: add Streamlit input form - gives users a working support interaction

- feat: add support dashboard views - exposes order, return, and stock information

- docs: add project report - records the problem, approach, and results

- audit: compile sprint history - makes board and commit activity traceable

- docs: add go-live readiness note - identifies limitations and handoff actions

# 12. Anti-Black-Box & Change-Control Rule

The assessment states that no board task may represent more than four hours of work. The team's ten agreed tasks therefore remain the official board units. If a task begins to exceed its estimate, the owner must immediately flag the issue rather than silently extending the task.

- First, identify why the task is expanding.

- Second, notify the team and record the issue.

- Third, if the work can no longer reasonably fit within the task's ≤4-hour scope, split the work into a clearly traceable additional unit only with team agreement and board documentation.

- Never hide additional work inside an existing task or create a retrospective audit trail.

# 13. Day 5 Delivery Checklist

☐ Working MVP / prototype covering the required ticket categories.

☐ End-to-end demo ready.

☐ Project Report complete and reviewed.

☐ Strategy Deck complete and reviewed.

☐ One-page Go-Live Readiness Note complete.

☐ Raw commit/edit and board audit evidence exported.

☐ Audit Log Compilation complete.

☐ Confidential Peer Reliability Index completed individually.

☐ Final self-assessment completed against the Day 1 baseline.

# 14. Team Sign-Off

| Member | Signature / confirmation | Date |
| --- | --- | --- |
| Nahom Tesfa | Nahom T. | 13/8/2026 |
| Eunice Livingproof | [Confirm] | [Date] |
| Hesborn Ombeka | [Confirm] | [Date] |
| Masombo Audrey | [Confirm] | [Date] |
| Faith Musyoka | [Confirm] | [Date] |